## Title Page
RD.045 MoSCoW List |  | <Document Reference Number>
2019-11-08 10:14
OUM
RD.045 MoSCoW List
<Company Long Name>
<Subject>
| Author: | <Author>
| Creation Date: | 2010-01-01
| Last Updated: | 2010-01-01
| Document Ref: | <Document Reference Number>
| Version: | 0.1
Approvals
| Approver | Signature
<Approver 1>
<Approver 2>
Note on D16: Automatically retrieved from Document Control worksheet
Note on D17: Automatically retrieved from Document Control worksheet
Note on D18: Automatically retrieved from Document Control worksheet
Note on D20: Automatically retrieved from Document Control worksheet

## General Instructions
RD.045 MoSCoW List |  |  |  |  | <Document Reference Number>
2019-11-08 10:14
General Instructions
1 | Use this template to create a MoSCoW (Must have, Should Have, Could Have, or Won't Have) Requirements Work Product.
2 | Also consider using this template as a traceability matrix. Additional Sheets have been provided after the MoSCoW sheet that will facilitate the traceability of high level requirements to functional requirements, to business rules, to Service Oriented Architecture, to Test Cases, as appropriate for individual projects.
3 | This work product is meant to scale up or down; under some conditions, you may want to merge work products from other tasks into this one as additional sheets. In some situations, the project may be very large, in that case, it is recommended that an automated tool is used such as Oracle Enterprise Repository, rather than using this spreadsheet to produce your work product.
4 | Each individual worksheet contains instructions on how it should be used. See cells with comments as indicated by the red triangle in the upper right corner of the cell.
|  | Condition | Approach
|  | SOA Services may be managed within a middleware tool or within the enterprise repository | You should review the task RA.025 Identify Candidate Services. You may choose to combine the spreadsheet from the RA.025 into this workbook for smaller projects.
|  | Scrum Product backlog and Sprint Backlog are included in this workbook | Project Managers using a Scrum approach to project management will use the last two sheets of this workbook for the Product Backlog and Sprint Backlog. Please review the Using Scrum in OUM White paper prior to using these sheets.

## Document Control
RD.045 MoSCoW List |  |  |  |  | <Document Reference Number>
2019-11-08 10:14
Document Control
Change Record
| Date | Author | Version | Change Reference
| 2010-01-01 | <Author> | 0.1
Reviewers
| No | Name | Position | Note
Note on B19: This column contains a formula. Just enter a name and the number will appear automatically.

## Product Backlog (Scrum)
Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | Database Creation | Must Have | US:101 | SQL Tables and Stored Procedures | Backend | Data Team
2 | Web API | Should Have | US:102 | Data Access Layer and Business Layer | Backend | Data and Service Team
3 | MVC | Should Have | US:103 | Presentation Layer | Frontend | Service and Presentation Team
4 | Testing and Reviewing | Should Have | US:104 | Test cases evaluation |  | Whole Team
5
6
7
8
9
10
11
12
13
14
Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.
Note on A3: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on B3: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on C3: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on D3: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on E3: Brief description of the requirements necessary to fulfill the objective
Note on F3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on G3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H3: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on I3: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on J3: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on K3: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on L3: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on M3: Column provides linkage to primary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on N3: Column provides linkage to secondary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on O3: Use column for supporting comments.
Note on P3: Column for defining the agreed upon acceptance criteria
Note on Q3: Description of the condition(s) that indicate the requirement has been satisfied.
Note on R3: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on S3: This column is used to provide supporting information, such as changes to the original requirement.

## Sprint Backlog (Scrum)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| US.101 | 1 | Deciding the number of tables to be created | Data Team | 01/11/2019 10:00 AM | 01/11/2019 12:00 AM | 01/11/2019 01:00 PM | Completed | 3 Hrs
|  | 2 | Discussion on fields of all tables and constraints required | Data Team | 01/11/2019 12:00 AM | 01/11/2019 04:00 PM | 01/11/2019 05:00 PM | Completed | 5 Hrs
|  | 3 | Query writing | Data Team | 02/11/2019 09:00 AM | 02/11/2019 02:00 PM | 02/11/2019 04:00 PM | Completed | 7 Hrs
| US.102 | 1 | Creating Entity | Data Team | 02/11/2019 03:00 PM | 02/11/2019 05:00 PM | 02/11/2019 06:00 PM | Completed | 3 Hrs
|  | 2 | Logic writing and setting up database connection for Employer and JobSeeker (Signup and login) | Data Team | 03/11/2019 09:00 AM | 04/11/2019 11:00 AM | 04/11/2019 01:00 PM | Completed | 14 Hrs
|  | 3 | logic writing for all the CRUD operations to be performed on the database | Service Team | 02/11/2019 09:00 AM | 04/11/2019 11:00 AM | 05/11/2019 11:00 AM | Completed | 31 Hrs
|  | 4 | Testing of Web API on Postman | Service Team and Data Team | 04/11/2019 09:00 AM | 04/11/2019 02:00 PM | 05/11/2019 10:00 AM | Completed | 10 Hrs
|  | 5 | Working on errors found | Service Team and Data Team | 04/11/2019 09:00 AM | 05/11/2019 10:00 AM | 05/11/2019 04:00 PM | Completed | 16.5 Hrs
| US.103 | 1 | Creating MVC Application | Presentation Team | 01/11/2019 09:00 AM | 01/11/2019 12:00 AM | 01/11/2019 01:00 PM | Completed | 4 Hrs
|  | 2 | Writing views for all the pages to be displayed | Presentation Team | 01/11/2019 12:00 AM | 04/11/2019 05:00 PM | 05/11/2019 01:00 PM | Completed | 29 Hrs
|  | 3 | Consume the Web API in MVC | Service Team | 03/11/2019 09:00 AM | 04/11/2019 05:00 PM | 05/11/2019 03:00 PM | Completed | 25 Hrs
|  | 4 | Testing the MVC views and connection | Presentation and service Team | 04/11/2019 09:00 AM | 04/11/2019 01:00 PM | 04/11/2019 01:00 PM | Completed | 4 Hrs
|  | 5 | Solving the errors observed | Presentation and service Team | 04/11/2019 02:00 PM | 05/11/2019 02:00 PM | 05/11/2019 04:00 PM | Completed | 11 Hrs
| US.104 | 1 | Testing the overall application on various test cases | Whole team | 06/11/2019 09:00 AM | 06/11/2019 02:00 PM | 06/11/2019 05:00 PM | Completed | 8 Hrs
|  | 2 | Modifying Application on the faults noticed | Whole team | 06/11/2019 03:00 PM | 07/11/2019 05:00 PM | 07/11/2019 08:00 PM | Completed | 14.5 Hrs
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.